## Construction Project Budget Tem
Cost code | Cost head | Budget (₹) | Committed (₹) | Actual to date (₹) | Balance (₹) | % used
MAT-01 | Cement, steel and aggregates | 18000000 | 14500000 | 11200000
MAT-02 | Finishing materials | 4500000 | 1200000 | 400000
LAB-01 | Labour — direct | 9000000 | 0 | 5100000
SUB-01 | Subcontract — MEP | 6500000 | 6500000 | 2300000
EQP-01 | Equipment hire and fuel | 2500000 | 900000 | 1350000
OVH-01 | Site overheads | 2000000 | 0 | 1100000
Total

## How to use
Construction Project Budget Template
• Balance uses the higher of committed and actual so open orders count against the budget.
• Review weekly alongside progress — % cost used should track % work done.
Free template from WebSoftOS — https://websoftos.com/templates/construction-budget
Want this automated? Start a free trial: https://websoftos.com/signup